## Team
Name | From Team | Start Date
Hemant Dhanawade | Practice | 2018-12-24
Anmol Rastogi | Practice | 2019-01-16
Pradip Uddhav Bobhate | NOV | 2019-02-05
Naresh Avaduta | NOV | 2019-02-05
Supriya Kare | Pune | 2019-02-15
Avinash Pandey | Pune | 2019-02-15
Shashikant Deore | Pune | 2019-03-04
Prem Kumar Khatri | Pune | 2019-03-08
Akshay Yadav | Pune | 2019-03-08
Onkar Kubal | Mumbai | 2019-03-06

## Team Activities
No. | Task | Description | Assigned To | Estimation In Days | Start Date | End Date | Status | Remark | Issues & Challenges
1 | Logging POC | Create POC for Database/File/Event Logging in the .net application | Hemant Dhanawade | 6 | 2018-12-24 | 2018-12-31 | Closed
2 | Cross Site Attack | Preventing Cross site scripting attack implementation in .net application. | Hemant Dhanawade | 6 | 2019-01-02 | 2019-01-11 | Closed
3 | Security Library Implementation | 1) Understand AES and DES Concept 2) Implementation of security library. | Hemant Dhanawade | 4 | 2019-01-10 | 2019-01-15 | Closed
4 | Caching POC | 1) Understand Redis Cache Concept 2) Create POC for caching in .net application. | Hemant Dhanawade | 6 | 2019-01-16 | 2019-01-25 | Closed
5 | LLD Document - Logging | Design Documentation | Hemant Dhanawade | 2 | 2019-02-01 | 2019-02-04 | Closed
6 | LLD Document - Caching | Design Documentation | Hemant Dhanawade | 2 | 2019-02-05 | 2019-02-06 | Closed
7 | Logging Library Implementation | This is a Logging Reusable Component, It should provides features like, 1) This library enables the logging activity in the .net application using NLog platform. 2) Multiple loggers (File/Database/Event) can be configure in the .net application. 3) Different types of messages like Debug, Error, Info, Warn and Fatal can be log. 4) Single action call to log messages using configured loggers in the .net application. | 1) Pradip Uddhav Bobhate 2) Naresh Avaduta | 7 | 2019-02-05 | 2019-02-28 | Closed
8 | Audit Log POC | Create POC for Audit Logging in the application. | 1) Anmol Rastogi 2) Hemant Dhanawade | 9 | 2019-02-05 | 2019-02-18 | Closed
9 | LLD Document - Audit Log | Design Documentation | 1) Anmol Rastogi 2) Hemant Dhanawade | 2 | 2019-02-15 | 2019-02-18 | Closed
10 | Angular UI POC | Create POC for Angular UI using existing Web API. | Sahil Arora | 5 | 2019-02-15 |  | WIP | All developed POC code is lost and we have started again from initial thought. | On Hold because of Azure machine issue. All developed POC code is on that machine if we lost that our 6-7 day effort will be waste and we have to start from initial thought
11 | Audit Log Library Implementation | This is an Audit Log Reusable Component, It will provides features like 1) This library enables the Audit log activity in the .net application. 2) It will provide standard way for audit log in the .net application. 3) All transactions in the application will be recorded in the audit log table (Structure provided in LLD). 4) It will provide feature to call any methods before save audit log from the .net application. 5) It will provide feature to call any methods after save audit log from the .net application. 6) It will provide feature to get individual record audit log report & all record audit log report in .net application. 7) It will store the audit log details in Json format in the .net application. | 1) Avinash Panday 2) Hemant Dhanawade | 6 | 2019-02-26 | 2019-03-06 | Closed
12 | Audit Log Library integration in K Framework tool | Audit Log library integration will contains, 1) Based on option selected by user on K framework screen the audit log functionality will be added in output .net project. 2) All required configuration will be added in output .net project. 3) Logging will be added in output .net project on defined activity which further can modify by developer. | Hemant Dhanawade | 5 | 2019-03-06 | 2019-03-15 | Closed | Extended because of other team activities
13 | Audit Log Report Implementation | Below reporte templete needs to be develop 1) Report should display entity audit report 2) Report should display Summarised report of all entity | Hemant Dhanawade | 5 | 2019-03-22 | 2019-04-03 | Closed
14 | Email Component POC | This component will have below features, 1) This component should be able to send to individual & multiple receipent. 2) Provision to send bulk email. 3) Provision to add attachment in email. 4) Provision to send HTML body in email. | Prem Kumar Khatri | 5 | 2019-03-08 |  | WIP | POC completed. Review Pending.
15 | Logging Enhancement - AWS Cloud Watch POC | This enhancement will have below features, 1) This will enable the .NET application to log application events in AWS. 2) It should have enhancement model for existing Logging component. 3) It should read application settings for AWS logging to log application events. | Akshay Yadav | 5 | 2019-03-08 | 2019-03-22 | Closed |  | AWS toolkit software installation required to Akshay. We are not getting updates from him related to activity on time. Technically he was not able to perform activity. Not talking responsibility for timely completion of activity.
16 | Logging Enhancement - Azure POC | Design Document which describes 1) Logging should be enabled in Azure with Application Insight | Akshay Yadav | 3 | 2019-03-14 | 2019-04-02 | Closed |  | VS 2015 upgradation was required to Akshay. We are not getting updates from him related to activity. Technically he was not able to perform this activity on time. Not talking responsibility for timely completion of activity. For each and every small activity he required help.
17 | Angular UI | Implement Angular UI which will be provided as option to Web Project |  | 25 |  |  | Open
18 | Data Caching | Designing POC for application caching enhancement for AWS Cloud watch caching |  | 6 |  |  | Open
19 | Data Caching | Designing POC for application caching enhancement for Azure caching |  | 7 |  |  | Open
20 | Workflow | Designing for Workflow component which will provide features, 1) Configurable workflow. 2) Exceptional workflow configuration. 3) Task wise user Dashboard | Nitin | 6 | 2019-03-15 |  | WIP |  | Discussion required by Hemant & Nitin with kedar to clear some doubts.
21 | Workflow | Implementation for Workflow component which will provide features, 1) Configurable workflow. 2) Exceptional workflow configuration. 3) Task wise user Dashboard |  | 20 |  |  | Open
22 | Cross site using Web API Issue | Cross site web api calling by jqgrid which is architectural issue. |  | 8 | 2019-04-03 |  | WIP
23 | Logging | Design Document which describes 1) Logging in AWS with Aws Cloud Watch |  | 3 |  |  | Open
24 | Exception Handling in Code Generator | Design Document to Add global error handling to the application's configuration. Add error handling at the application, page, and code levels. Log errors for later review. Display error messages that do not compromise security. |  | 5 |  |  | Open
25 | Exception Handling in Code Generator | Implement Exception Handling in the Code Generator Framework. |  | 5 |  |  | Open
26 | Security Component | Designing Security Features 1) Authorization Filter so every request will authorize before process |  | 5 |  |  | Open
27 | Security Component | Designing Security Features 1) Manage User, Role, Users and Authorization Filter Utility for Password hash/salt key |  | 5 |  |  | Open
28 | Security Component | Implement Authorization Filter so every request will authorize before process |  | 5 |  |  | Open
29 | Security Component | Implement Manage User, Role, Users and Authorization Filter |  | 5 |  |  | Open
30 | Security Component | Implement Utility for Password hash/salt key |  | 1 |  |  | Open
31 | UI Templates | Design 23 UI Templates |  | 12 |  |  | Open
32 | UI Templates | Implement all UI 23 UI Templates as HTML with Bootstrap |  | 22 |  |  | Open
33 | UI Templates | Integrate all 23 Templates in the Code Generator Framework. |  | 15 |  |  | Open
34 | Email Component | Implement Email component |  | 3 |  |  | Open
35 | Logging Component | Implementation of application event logging enhancement to AWS CloudWatch |  | 6 |  |  | Open
36 | Logging Component | Implementation of application event logging enhancement to Azure logging |  | 5 |  |  | Open
37 | Testing | Regression Testing |  | 10 |  |  | Open
38 | Testing | Bug Fixes |  | 5 |  |  | Open
39 | Validations in K Framework | Check whether validation required in the application generate from K foundation tool apart from existing validations. |  | 3 |  |  | Open

## Issues & Challenges
Sr No | Issues/Challenges | Status | Meeting Date | Decision
1 | Azure virtual machine issue. Angular developed POC code is on that machine if we lost that our 6-7 day effort will be waste and we need to develop it from start. Waiting for confimation from Kedar. | Closed | 2019-03-28 | We have lost all the changes, we are not able to recover those because of KPIT subscription is changed to Birlasoft subscription
2 | Task related to AWS logging & Azure logging was assigned to Akshay Yadav and gave him 2 weeks time. But we are not getting updates from him related to activities on time. Technically he was not able to perform activities and not talking responsibility for timely completion of activity. For each and every small activity he required help. Sometime almost whole day he was not available on Mail as well as Chat. | Closed | 2019-03-27 | Discontinued him from further Activity, AWS PoC is complete,
3 | Discussion required by Hemant & Nitin with Kedar to clear some doubts related to workflow design for completion. | Open |  | Let’s Plan it On Monday 1st April Morning 10:00 AM Put Meeting Invite
4 | Prem has developed the Email POC component and after completion now he is not working on K framework so after code review the changes has to be done by someone else from team after understanding it properly which will take time. | Open
5 | Currently only Hemant is working on development activity of K framework so other activities will take time for completion. | Open |  | Let’s Complete your activity regarding Audit log and shared status by Tomorrow
6 | Task related to AWS caching was assigned to Avinash Panday but he was working on this activity in off business hours at home because of network issues he was not able to work on this activity and he is facing some technical issue for this we are not able connect to each other as he work off business hour on this activity. | Open

## Other Activities
Sr No | Task | Status
1 | The dropdown on generated application screen of table creates based on Primary-Foreign Key relation & few conditions written in code - Just for Understanding. | Closed
2 | Restrict html value in property of view on view input - Checked it doesn't exist .net core 2.2. | Closed
3 | Check whether for API encoding is required - Not required it will done later by developer. | Closed
4 | Install SQL express on machine 137.117.81.193 for hosting test site. | Closed
5 | Hosting of test site on machine 137.117.81.193 for testing cross site attack issue. | Closed

## Bug Fixes
Sr No | Bug | Status
1 | Data inserting issues in identity column of table in database is resolved and implemented in tool | Closed
2 | Designed home page for testing cross site attack | Closed
3 | Partial View was not loaded properly because of unsupported patial view path in @Html.Partial("") | Closed
4 | Bundle config will need BuildBundlerMinifier nuget package to work in asp.net core 2.2 | Closed
5 | Web API and Web APP Port mismatch in launch config because of this web app & web api was not working properly together | Closed

## Infrastructure
Machine IP | 137.117.81.193
Machine URL | kpitmsplab001.eastus.cloudapp.azure.com
Azure UserName | kpit-msp-lab@outlook.com
Azure Password | kpit@1234
Test Site URL | http://kpitmsplab001.eastus.cloudapp.azure.com/

## Reporting
No. | Activities | Description | Assigned To | Activity Start Date | Actual End Date | Status | Remark
1 | Logging POC | Create POC for Database/File/Event Logging in the .net application | Hemant Dhanawade | 2018-12-24 | 2018-12-31 | Closed
2 | Cross Site Attack | Preventing Cross site scripting attack implementation in .net application. | Hemant Dhanawade | 2019-01-02 | 2019-01-11 | Closed
3 | Security Library Implementation | 1) Understand AES and DES Concept 2) Implementation of security library. | Hemant Dhanawade | 2019-01-10 | 2019-01-15 | Closed
4 | Caching POC | 1) Understand Redis Cache Concept. 2) Create POC for caching in .net application. | Hemant Dhanawade | 2019-01-16 | 2019-01-25 | Closed
5 | LLD Document - Logging | Design Documentation | Hemant Dhanawade | 2019-02-01 | 2019-02-04 | Closed
6 | LLD Document - Caching | Design Documentation | Hemant Dhanawade | 2019-02-05 | 2019-02-06 | Closed
7 | Logging Library Implementation | This is a Logging Reusable Component, It should provide features like, 1) This library enables the logging activity in the .net application using NLog platform. 2) Multiple loggers (File/Database/Event) can be configure in the .net application. 3) Different types of messages like Debug, Error, Info, Warn and Fatal can be log. 4) Single action call to log messages using configured loggers in the .net application. | 1) Pradip Uddhav Bobhate 2) Naresh Avaduta | 2019-02-05 | 2019-02-28 | Closed
8 | Audit Log POC | Create POC for Audit Logging in the application. | 1) Anmol Rastogi 2) Hemant Dhanawade | 2019-02-05 | 2019-02-18 | Closed
9 | LLD Document - Audit Log | Design Documentation | 1) Anmol Rastogi 2) Hemant Dhanawade | 2019-02-15 | 2019-02-18 | Closed
10 | Angular UI POC | Create POC for Angular UI using existing Web API. | Sahil Arora | 2019-04-03 |  | WIP | All developed POC code is lost and we have started again from initial thought.
11 | Audit Log Library Implementation | This is an Audit Log Reusable Component, It will provides features like 1) This library enables the Audit log activity in the .net application. 2) It will provide standard way for audit log in the .net application. 3) All transactions in the application will be recorded in the audit log table (Structure provided in LLD). 4) It will provide feature to call any methods before save audit log from the .net application. 5) It will provide feature to call any methods after save audit log from the .net application. 6) It will provide feature to get individual record audit log report & all record audit log report in .net application. 7) It will store the audit log details in Json format in the .net application. | 1) Avinash Panday 2) Hemant Dhanawade | 2019-02-26 | 2019-03-06 | Closed
12 | Audit Log Library integration in K Framework tool | Audit Log library integration will contains, 1) Based on option selected by user on K framework screen the audit log functionality will be added in output .net project. 2) All required configuration will be added in output .net project. 3) Logging will be added in output .net project on defined activity which further can modify by developer. | Hemant Dhanawade | 2019-03-06 | 15-Mar-19 | Closed | Delayed because of other team activities.
13 | Audit Log Report Implementation | Below reporte templete needs to be develop 1) Report should display entity audit report 2) Report should display Summarised report of all entity | Hemant Dhanawade | 2019-03-22 | 2019-04-03 | Closed
13 | Email Component POC | This component will have below features, 1) This component should be able to send to individual & multiple receipent. 2) Provision to send bulk email. 3) Provision to add attachment in email. 4) Provision to send HTML body in email. | Prem Kumar Khatri | 2019-03-08 |  | WIP | POC completed. Review Pending.
14 | Logging Enhancement - AWS Cloud Watch POC | This enhancement will have below features, 1) This will enable the .NET application to log application events in AWS. 2) It should have enhancement model for existing Logging component. 3) It should read application settings for AWS logging to log application events. | Akshay Yadav | 2019-03-08 | 2019-03-22 | Closed | Delayed Because of below reasons, 1. AWS toolkit software installation required to Akshay. 2. Proper updates related to activity was not getting. 3. Technically Akshay was not able to perform activity. 4. Not talking responsibility for timely completion of activity.
15 | Logging Enhancement - Azure POC | Design Document which describes 1) Logging should be enabled in Azure with Application Insight | Akshay Yadav | 2019-03-14 | 2019-04-02 | Closed | Delayed Because of below reasons, 1. AWS toolkit software installation required to Akshay. 2. Proper updates related to activity was not getting. 3. Technically Akshay was not able to perform activity. 4. Not talking responsibility for timely completion of activity.
17 | Angular UI | Implement Angular UI which will be provided as option to Web Project |  |  |  | Open
18 | Data Caching | Designing POC for application caching enhancement for AWS Cloud watch caching |  |  |  | Open
19 | Data Caching | Designing POC for application caching enhancement for Azure caching |  |  |  | Open
20 | Workflow | Designing for Workflow component which will provide features, 1) Configurable workflow. 2) Exceptional workflow configuration. 3) Task wise user Dashboard | 1) Nitin 2) Hemant Dhanawade | 2019-03-15 |  | WIP
21 | Workflow | Implementation for Workflow component which will provide features, 1) Configurable workflow. 2) Exceptional workflow configuration. 3) Task wise user Dashboard |  |  |  | Open
22 | Cross site using Web API Issue | Cross site web api calling by jqgrid which is architectural issue. | Hemant Dhanawade | 2019-04-03 |  | WIP
23 | Logging | Design Document which describes 1) Logging in AWS with Aws Cloud Watch |  |  |  | Open
24 | Exception Handling in Code Generator | Design Document to Add global error handling to the application's configuration. Add error handling at the application, page, and code levels. Log errors for later review. Display error messages that do not compromise security. |  |  |  | Open
25 | Exception Handling in Code Generator | Implement Exception Handling in the Code Generator Framework. |  |  |  | Open
26 | Security Component | Designing Security Features 1) Authorization Filter so every request will authorize before process |  |  |  | Open
27 | Security Component | Designing Security Features 1) Manage User, Role, Users and Authorization Filter Utility for Password hash/salt key |  |  |  | Open
28 | Security Component | Implement Authorization Filter so every request will authorize before process |  |  |  | Open
29 | Security Component | Implement Manage User, Role, Users and Authorization Filter |  |  |  | Open
30 | Security Component | Implement Utility for Password hash/salt key |  |  |  | Open
31 | UI Templates | Design 23 UI Templates |  |  |  | Open
32 | UI Templates | Implement all UI 23 UI Templates as HTML with Bootstrap |  |  |  | Open
33 | UI Templates | Integrate all 23 Templates in the Code Generator Framework. |  |  |  | Open
34 | Email Component | Implement Email component |  |  |  | Open
35 | Logging Component | Implementation of application event logging enhancement to AWS CloudWatch |  |  |  | Open
36 | Logging Component | Implementation of application event logging enhancement to Azure logging |  |  |  | Open
37 | Testing | Regression Testing |  |  |  | Open
38 | Testing | Bug Fixes |  |  |  | Open
39 | Validations in K Framework | Check whether validation required in the application generate from K foundation tool apart from existing validations. |  |  |  | Open